## Time line
Week | Duration | Milestone
Week1 | 27-Jul-2026 to 02-Aug-2026 | Planning, Collection, Cleaning
Week2 | 03-Aug-2026 to 10-Aug-2026 | Transform, Model, DAX, Dashboard, Testing
Sprint | Sprint 1
Project | SynapseSCM: Enterprise Supply Intelligence Platform
Module | Procurement Cost Intelligence
Start | 2026-07-27
End | 2026-08-08
Goal | Develop Phase 1 Procurement Cost Intelligence Dashboard
Status | In Progress
Overall Progress | 98%

## Phase1 Project plan
Phase | Task | Start | End | Status | % | Remarks
Planning | Finalize Project Scope | 2026-07-27 | 2026-07-27 | Completed | 100 | Project scope finalized
Business | Business Requirements & KPIs | 2026-07-27 | 2026-07-27 | Completed | 100 | BRD and KPIs prepared
Data | Collect Internal Datasets | 2026-07-28 | 2026-07-28 | Completed | 100 | ERP datasets collected
Data | Collect External Live Datasets | 2026-07-29 | 2026-07-29 | Completed | 100 | Live market datasets collected
Data | Clean, Validate & Organize Datasets | 2026-07-30 | 2026-08-01 | Completed | 100 | Internal and external datasets cleaned and validated
Power Query | Data Transformation | 2026-08-02 | 2026-08-02 | Completed | 100 | Data types standardized and transformations applied
Power Query | Merge & Shape Data | 2026-08-03 | 2026-08-03 | Completed | 100 | Merge datasets and prepare analytical model
Power BI | Create Data Model | 2026-08-04 | 2026-08-04 | Completed | 100 | Create relationships and star schema
Power BI | Develop DAX Measures & KPIs | 2026-08-05 | 2026-08-06 | Completed | 100 | Create business measures and KPIs
Power BI | Build Dashboard | 2026-08-07 | 2026-08-07 | Completed | 100 | Executive dashboard and analytical visuals
Testing | Dashboard Testing & Validation | 2026-08-08 | 2026-08-08 | Completed | 100 | Validate calculations and business insights
Documentation | README & Final Documentation | 2026-08-08 | 2026-08-08 | Completed | 100 | Complete project documentation and final review

## Dailt project progress
Date | Phase 1 Planned Task | Completed Work | Hours Spent | Next Day Plan
2026-07-27 | Finalize project scope and business requirements | Completed | 3 | Collect internal and external datasets
2026-07-28 | Collect internal datasets | Completed | 3 | Collect external live datasets
2026-07-29 | Collect external live datasets | Completed | 3 | Clean internal datasets
2026-07-30 | Clean internal datasets | Completed | 3 | Clean external live datasets
2026-07-31 | Clean external live datasets | Completed | 3 | Validate and organize cleaned datasets
2026-08-01 | Validate and organize cleaned datasets | Completed | 3 | Perform Power Query data transformations
2026-08-02 | Power Query – Data Transformation | Completed | 3 | Merge and shape data in Power Query
2026-08-03 | Power Query – Merge & Shape Data | Completed | 3 | Create Power BI data model
2026-08-04 | Create Power BI Data Model | Completed | 3 | Develop DAX measures and KPIs
2026-08-05 | Create DAX Measures & KPIs | Completed | 3 | Continue advanced DAX development
2026-08-06 | Continue DAX Development | Completed | 3 | Build Dashboard – Executive Overview (Page 1)
2026-08-07 | Build Dashboard – Page 1 & Additional Pages | Completed | 4 | Test dashboard and validate insights
2026-08-08 | Dashboard Testing, Documentation, README & Final Review | Completed | 4 | Project Submission